Requirements Workshop Work Breakdown Structure

Reference Introduction to Part II in

Requirements by Collaboration by Ellen Gottesdiener, Addison-Wesley, 2002.

Phase 1: Plan

Stage 1:	Define Workshop Purpose and Participants

Tangible Deliverables: Workshop Purpose Statement

Tasks

- Gather information from initial contact.

- Identify workshop and project sponsor.

- Assemble a planning team.

- Gather information from sponsors.

- Characterize project.

- Identify potential participants, recorder, and observers.

- Draft initial purpose statement.

- Gather information from participants and planning team.

- Identify recorder.

- Identify observers and on-call subject matter experts.

- Conduct participant interviews.

- Identify workshop time constraints.

- Select requirements navigation strategy.

- Decide whether multiple workshops are needed.

- Refine the workshop purpose statement.

- Schedule workshop participants.

Stage 2:	Define Workshop Principles, Products, Place, Process

Tangible Deliverables: Workshop Agenda

Tasks

- Define decision rule and decision rule process.

- Draft generic and special principles (ground rules).

- Identify tangible and intangible workshop deliverables.

- Identify level of detail needed for all workshop products.

- Identify workshop inputs (draft models, documentation, pre-work, templates, and workshop aids such as instructions and samples).

- Delineate doneness tests for deliverables.

- Design workshop process: opener, activities, and closer.

- Identify and schedule workshop place.

- Arrange for workshop refreshments.

- Schedule sponsor for kick-off and show-and-tell.

- Draft workshop agenda.

Stage 3:	Prepare Workshop Inputs

Tangible Deliverables: Workshop Inputs

Tasks

- Create draft models of workshop input materials.

- Design workshop pre-work materials and instructions.

- Acquire or collect templates, workshops, and modeling guidelines.

- Identify system and user documentation needed.

- Review draft workshop agenda with sponsor and participants.

- Prepare workshop pre-work materials.

- Revise draft agenda.

- Create visual tools such as posters.

- Acquire materials and tools for the workshop room.

- Select final workshop evaluation form.

- Arrange for workshop repository.

Stage 4:	Orient Participants

Tangible Deliverables: Final Workshop Agenda

Tasks

- Assess the need for an orientation meeting.

- Schedule orientation.

- Prepare for and conduct orientation.

- Adjust workshop agenda if necessary.

- Prepare and distribute final workshop agenda.

Phase 2: Conduct: Do

Stage 1:	Prepare Workshop Room

Tangible Deliverables: Workshop Room Ready to Go

Tasks

- Arrange tables and chairs.

- Hang posters.

- Prepare walls.

- Ensure that refreshments are available.

- Test equipment.

- Make workshop tools accessible (markers, cards, sticky notes).

- Greet participants.

Stage 2:	Open Workshop

Tangible Deliverables: none

Tasks

- Conduct sponsor kickoff.

- Review purpose, principles (test decision rule process), and products.

- Explain process roles (facilitator and recorder).

- Review agenda.

- Obtain pre-work materials from participants.

- Conduct opener activity.

Stage 3:	Conduct Workshop

Tangible Deliverables: Requirements Models

Tasks

- Facilitate workshop.

- Adjust workshop process to deliver products.

- Maintain workshop parking lot or issues list.

- Record workshop content.

- Conduct interim workshop evaluations.

- Prepare for show-and-tell.

Stage 4:	Close Workshop

Tangible Deliverables:

Assigned Issues and Dates, Documented List of Next Steps, Completed Workshop Evaluation Forms or Poster

Tasks

- Conduct show-and-tell.

- Review workshop products list against actual deliverables.

- Review and assign remaining issues.

- Define and assign post-workshop actions.

- Complete workshop evaluation.

Phase 3: Assess: Check

Stage 1:	Review Evaluations

Tangible Deliverables: Summary of Evaluations

Tasks

- Read workshop evaluations and debriefing documentation from the session.

- Conduct self-assessment.

- Deliver copy of evaluations to workshop sponsor and planning team.

- Debrief immediate learning point with sponsor and planning team.

Stage 2:	Complete Post-Workshop Assignments

Tangible Deliverables: Completed Parking Lot or Issues Documentation, Completed Actions and Associated Documentation

Tasks

- Research issues.

- Document issues to all participants.

- Close issues and communicate issue resolutions.

- Conduct action steps.

- Document action steps.

- Close actions and communicate actions.

- Close outstanding requirements models per issues and actions.

Stage 3:	Publish and Review Workshop Documentation

Tangible Deliverables: Edited Workshop Documentation

Tasks

- Generate or post documentation from workshop.

- Distribute workshop documentation.

- Edit and annotate workshop documentation.

- Update documentation.

- Redistribute final copy of documentation.

Phase 4: Improve Facilitation Process: Act

Stage 1:	Plan Next Steps and Workshops

Tangible Deliverables: Project Action Plan, Next Workshop Schedule

Tasks

- Define next steps for using workshop deliverables in project activities.

- Assess need for additional workshop or adjustment to existing workshop plan.

- Schedule workshop(s) as warranted.

- Begin planning process (Phase 1).

Stage 2:	Assess Business Value

Tangible Deliverables: Cost-Benefit Analysis

Tasks

- Analyze and estimate workshop costs (person time, project lapse time, actual funds).

- Estimate costs for non-workshop alternatives.

- Interview sponsors, stakeholders, and participants as needed.

- Estimate benefits and value.

- Prepare and present cost-benefit analysis.

- Prepare and distribute post-workshop evaluation (four to eight weeks later).

- Read and summarize evaluations.

- Conduct self-assessment.

- Summarize workshop data (before, during, after).

- Determine improvement opportunities: goals, questions, metrics.

- Determine data to capture.

- Draft changes in process, aids, templates, or methodology.

- Obtain feedback on proposed changes.

- Implement changes.

Stage 3:	Adjust Facilitation Process

Tangible Deliverables: Documented Changes

Tasks

- Draft changes to process, documentation, tools.

- Approve changes.

- Communicate changes.

- Implement changes.

- Monitor metrics against goals.